PROJECT PLANNING PHASE

Product Backlog • Sprint Planning • User Stories • Story Points

| Project Detail | Value |
| --- | --- |
| Date | 15 October 2026 |
| Team ID | 23891A0578 |
| Project Name | Medical Diagnosis Center – ServiceNow Application |
| Maximum Marks | 5 Marks |

1. Product Backlog, Sprint Schedule, and Estimation (4 Marks)

The backlog below is adapted from the Medical Diagnosis Center project specification. Story points are planning estimates, not recorded completion results.

| Sprint | Functional Requirement (Epic) | Story ID | User Story / Task | Points | Priority |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Patient Registration | US-01 | As a patient, I can create and maintain a profile with contact details. | 3 | High |
| Sprint 1 | Diagnostic Test Catalog | US-02 | As a patient, I can view active tests, categories, descriptions, duration, and price. | 3 | High |
| Sprint 1 | Test Booking | US-03 | As a patient, I can book a test by selecting a test, date, and available time slot. | 5 | High |
| Sprint 1 | Booking Validation | US-04 | As the system, I validate required fields and prevent duplicate or overlapping bookings. | 5 | High |
| Sprint 1 | Appointment Management | US-05 | As a patient, I can view my appointments and request cancellation or rescheduling. | 4 | High |
| Sprint 2 | Approval Workflow | US-06 | As a lab manager, I can review and approve or reject special tests when approval is required. | 4 | Medium |
| Sprint 2 | Appointment Workflow | US-07 | As staff, I can update appointment status from Requested through Confirmed and Sample Collected. | 4 | High |
| Sprint 2 | Processing & Status | US-08 | As staff, I can track Processing, Completed, and Report Available states for each appointment. | 4 | High |
| Sprint 2 | Email Notifications | US-09 | As a patient, I receive booking, approval, cancellation, and report-availability notifications. | 4 | High |
| Sprint 2 | Role-Based Access | US-10 | As an administrator, I can restrict access according to patient, staff, and admin roles. | 4 | High |
| Sprint 3 | Report Management | US-11 | As a lab technician or doctor, I can create and verify a report linked to an appointment. | 5 | High |
| Sprint 3 | Report Download | US-12 | As a patient, I can securely view or download my available diagnostic report. | 4 | High |
| Sprint 3 | Cancellation & Refund | US-13 | As the system, I calculate a refund after a 10% cancellation charge and store the refund amount. | 3 | Medium |
| Sprint 3 | Data Architecture | US-14 | As an administrator, I can maintain patient, diagnostic test, appointment, and report records. | 4 | High |
| Sprint 4 | Admin Dashboard | US-15 | As a manager, I can view test volumes, revenue indicators, and operational performance. | 5 | Medium |
| Sprint 4 | Booking Rules | US-16 | As an administrator, I can configure slot capacity, advance-booking limits, and cut-off rules. | 4 | High |
| Sprint 4 | Audit & Escalation | US-17 | As a manager, I can review status history and receive alerts for delayed report processing. | 4 | Medium |
| Sprint 4 | User Acceptance Testing | US-18 | As a stakeholder, I can validate the system before release. | 4 | High |

2. Project Tracker, Velocity & Sprint Schedule (4 Marks)

The schedule below is a proposed plan. Enter actual completed points and release dates after each sprint; no completion data has been assumed.

| Sprint | Planned Story Points | Duration | Start Date (Planned) | End Date (Planned) | Points Completed | Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | 20 | 6 days | 16 Oct 2026 | 21 Oct 2026 | To be updated | To be updated |
| Sprint 2 | 20 | 6 days | 22 Oct 2026 | 27 Oct 2026 | To be updated | To be updated |
| Sprint 3 | 16 | 6 days | 28 Oct 2026 | 02 Nov 2026 | To be updated | To be updated |
| Sprint 4 | 17 | 6 days | 03 Nov 2026 | 08 Nov 2026 | To be updated | To be updated |

Velocity Calculation

Example based on the planning template: if a team completes 20 story points during a 10-day sprint, average velocity per day is:

Average velocity = Story points completed ÷ Sprint duration = 20 ÷ 10 = 2 story points/day

For a 6-day sprint, the estimated capacity at that rate is:

2*6=12 story points

For this project, calculate actual velocity at the end of each sprint using completed story points divided by the sprint duration. The planned 20 points per sprint are estimates and should be revised using the team’s actual results.

Burndown Chart

A burndown chart tracks the amount of work remaining against time during a sprint. For the Medical Diagnosis Center project, use the sprint backlog’s remaining story points to update the chart each day. A downward trend toward zero indicates progress toward completing the sprint scope.

Suggested chart inputs: sprint day on the horizontal axis; remaining story points on the vertical axis; include a planned-work line and an actual-work line. Record actual values during the sprint rather than inventing completion data.

3. Scope Covered by the Backlog

| Area | Project Requirement |
| --- | --- |
| Patient-facing portal | Home page, test catalog, patient profile, test booking, appointments, report access, and notifications. |
| Booking and scheduling | Real-time slot validation, capacity controls, prevention of overlapping bookings, advance booking and cut-off rules. |
| Workflow and staff operations | Approval where required; status flow from Requested and Confirmed through Sample Collected, Processing, Completed, and Report Available; cancellation handling. |
| Reports and payments | Report records and attachments linked to patients and appointments; optional payment support; refund calculation with a 10% cancellation charge as described in the source. |
| Administration and assurance | Role-based access, audit trail, delayed-report escalation, management dashboard, user acceptance testing, and deployment checks. |